## Sheet1
Function Category | Requirement | Owner | Workload(hours) | Deadline | Status | Complete time
Requirements Analysis and design |  | Haitao |  |  | 100%
Requirements Analysis |  | Haitao (Guolei, Weifeng, Chenxu) | 16 | 2019-12-27 | 100% | 2019-12-27
database design |  | Weifeng (Chenxu, Haitao) | 8 | 2019-12-31 | 100% | 2019-12-31
api design |  | Weifeng (Chenxu, Haitao) | 4 | 2019-12-31 | 100% | 2019-12-31
Android App Development |  | Chen xu
Dev environment prepare |  | Chen xu | 8 | 2019-12-27 | 100% | 2019-12-27
Main Page |  | Chen xu | 4 |  | 100%
loading page |  | Chen xu | 2 |  | 100%
auth key input page (UI only) |  | Chen xu | 8 |  | 0%
visit process (UI only) | 1. checkin,2.search employee 3. call | Chen xu | 20 |  | 0%
Deliver (UI only) |  | Chen xu | 8 | 2020-01-09 | 0%
auth key input page (api integration) |  | Chen xu | 8 |  | 0%
visit process (api integration) | 1. checkin,2.search employee 3. call | Chen xu | 16 |  | 0%
Deliver (api integration) |  | Chen xu | 8 | 2020-01-15 | 0%
functions testing & fix bugs |  | Chen xu | 24 | 2020-01-20 | 0%
Admin Website Development(include api integration) |  | Weifeng
Dev environment prepare |  | Weifeng | 8 | 2019-12-27 | 100% | 2019-12-27
main page, login(sso) and logout | All webpages, layouts, styles. | Weifeng | 8 |  | 0%
account_management | add, edit,delete user account for different roles | Weifeng | 4 |  | 0%
auth key setting | edit auth key(including autherization process coding.) | Weifeng | 4 |  | 0%
contact maintaince | search, add, edit, delete | Weifeng | 4 |  | 0%
contact import and export | by excel | Weifeng | 6 |  | 0%
visit reason maintaince |  | Weifeng | 2 |  | 0%
visit_history | search | Weifeng | 4 |  | 0%
deliver_contact maintaince | edit auth key deliver contact | Weifeng | 3 |  | 100%
API Development |  | Weifeng |  |  | 90% | 2020-01-07
API for app | Contact Management | Weifeng | 8 |  | 90%
| Delivery Contact | Weifeng | 2 |  | 90%
| Visit History | Weifeng | 4 |  | 90%
| Autherization (Frontend - Backend) | Weifeng | 8 |  | 90%
API for website | Web site enviroment deploying. | Weifeng | 10 |  | 90%
| SSO deployment and Testing | Weifeng | 8 |  | 90%
Sum |  |  | 217
| Dev | weifeng | 83 | 2020-01-15
| Dev | chen xu | 106 | 2020-01-20